## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature | Feature | Feature
Date of milestone | Nov 10 2019 | Nov 10 2019 | Nov 10 2019 | Nov 10 2019 | Nov 10 2019 | Nov 10 2019
Features in scope | Authentication/Login | Manage Camp Dates | Manage Camp Bookings | Make Camp Bookings (Schools) | Make Camp Bookings (Organisations) | Validate Google Vision OCR (Optical Character Recognition) AI & ML API
Features implemented | Authentication/Login | Manage Camp Dates | Manage Camp Bookings | Make Camp Bookings (Schools) | Make Camp Bookings (Organisations) | Validate Google Vision OCR (Optical Character Recognition) AI & ML API
Features in deficit this Iteration
Iteration Comments & Summary | Implemented authentication with user roles etc. to allow access to Admin/Lecturer user features. | Added CRUD functions for Lecturers to manage Camp Dates. Lecturers can now add, view list of, delete & edit dates which they are available for school camps. | Added CRUD functions for Lecturers to manage Camp Bookings. Lecturers can now add, view list of, delete & edit camp bookings made by schools/organisations. | Added function for Schools to use their unique school roll number to make camp bookings. | Added function for Organisations without roll numbers, to make camp bookings. | I was able to validate that the API works within .Net C# system. Tested sending images/PDFs with hand-written text and the correct string or JSON is returned from API.
Iteration #2
Date of milestone
Features in scope
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #3
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary